## Sheet1
Task | Days Before Event | Deadline | Assignments | Notes
Plan event theme and goals | 365 | 2016-08-04 |  |  | Event date: | 2017-08-04
Secure venue | 300 | 2016-10-08
Determine food arrangements | 280 | 2016-10-28
Event and save the date announcement (social media) | 270 | 2016-11-07
(Sponsor or program advertising campaign begins?) | 270 | 2016-11-07 |  | If you have prospective sponsors or advertisers in the print program, now is the time to reach out to them with a description of the event and a direct ask for how you would like for them to help (e.g., various levels of sponsorship and their benefits, various sizes of ads in the program and their costs, etc.)
Calls for programming (workshop proposals, etc.) | 220 | 2016-12-27
Deadline for programming proposals | 190 | 2017-01-26
Select programming and notify approved presenters | 185 | 2017-01-31
Develop event schedule | 148 | 2017-03-09
Determine ticket pricing | 145 | 2017-03-12
Set up registration system | 140 | 2017-03-17
Open registration | 120 | 2017-04-06
Marketing: social media and web begins | 120 | 2017-04-06
Marketing: posters/flyers and networking | 118 | 2017-04-08
Close registration | 10 | 2017-07-25
(Sponsor or program advertising campaign ends) | 10 | 2017-07-25 |  | Deadline for sponsorships and ads, so they can be entered in the print program
(confirm final numbers with caterer) | 9 | 2017-07-26 |  | If providing food through a caterer
Design event print program | 8 | 2017-07-27 |  | Be sure to include acknowledgement of sponsors and other major supporters
Print event programs and any onsite signage | 7 | 2017-07-28
Print out gate lists for registration table | 3 | 2017-08-01
(Grocery shopping) | 2 | 2017-08-02 |  | If providing food through a meal plan
2017-08-04
2017-08-04
2017-08-04
2017-08-04
Transport supplies onsite | 1 | 2017-08-03
Day 1 of event | 0 | 2017-08-04
Formulas:
Deadline = EventDate-[Days Before Event]
Note on B1: Mark Green: You can change these if you like; deadline will update
Note on C1: Date by which the task should be completed. Do not change these by hand; change the number of days before the event instead, and the deadline will update automatically
Note on D1: Who is assigned to perform the task
Note on G2: Change this date, all deadline dates will update